## PMHandBook
Phase | Key Actors | Entry Criteria | Activity | Deliverables | Exit Criteria
Discovery | BA, Architect, Tech Lead, PM | 1. Signed SOW 2.Discovery Plan | 1. Requirement details and User Stories 2. UI definition 3. Integration touch point identification 4. Data source Identification 5. Process flow diagram 6. End User Profile Matrix 7. Report Requirements capture (use existing template) 8. RACI 9. Escalation Matrix | 1. Discovery Kick Off Deck 2. Functional Requirements document | 1. Signed Off FRD 2. Project Plan finalized with clearly stated dependency on customer / other teams 3. CR for the gap identified (if any)
Design | BA, Architect, Tech Lead, PM | 1.Signed Off FRD 2. Final Project plan and schedule | 1. Flowchart 2. Data model 3. Wireframe 4. Deployment planning 5. Integration strategy 6. Data Migration strategy | 1. Technical Design document 2. Traceability Matrix 3. Deployment plan | Design reviewed (internal & Customer)and signed Off
Build, Unit Test, Functional Test | BA, Architect, Tech Lead, SFDC Developer, Senior developer, Test Analyst, PM | 1.Signed Off Design 2.User Stories | 1. Build iteration in dev org 2. Unit testing 3. Functional testing -Test Cases, Test Scenarios 4. Code review and review log 5. SIT Plan signed Off by all parties involved | 1. Test Cases 2. Test log 3. Final Technical Design document | 1. Code review log, Internal 2. Code review with Customer (if any) 3. Test logs, QA Sign-Off on Functional Testing 4. Code movement to SIT
SIT | BA, Architect, Tech Lead, SFDC Developer, Senior developer, Test Analyst, PM | 1. Code deployed in SIT 2. Sample data loaded in SIT 3. QA Sign-Off on Functional Testing 4. Integrations interfaces active on SIT | 1. End to end functional testing 2. Testing Integration touchpoints 3. Training PPT preparation | 1. Test Logs 2. Code fixes | 1. Test log 2. Code fixes in Dev 3. Code fixes migrated to SIT box 4. QA Sign-Off on SIT 5. Code movement to UAT
Train the Trainer | BA | 1. Stable code in SIT | 1. Sample User Credential in SIT for Training 2.Training Delivery | Impart Training & help Users with hands On sessions | Successful completion of Training
Regression Testing(if needed) | Tech Lead, SFDC Developer, Senior developer, Test Analyst, PM | Stable code in SIT | 1. Existing functionality tested by Customer 2. Test logs 3. Defect fixes | Test logs | End to end tested code (mayb with existing known defects)
UAT | BA, Architect, Tech Lead, SFDC Developer, Senior developer, Test Analyst, PM | 1. Code deployed in UAT 2. Prod like data loaded in UAT 3. QA Sign-Off on SIT 4. Integrations interfaces active on UAT | 1. Profile based process testing by selected Users 2. Bug Triage 3. Test logs 4. Fixes 5. Performance Testing | 1. UAT kick Off 2.Test logs | 1. UAT test log (profile based) 2. UAT fixes in Dev, migrated to UAT 3. UAT Sign Off by Customer
Data Migration | BA, Architect, Tech Lead, SFDC Developer, PM | 1. Source and Target mapping document 2. Template prepared for data 3. Data shared by customer in templates 4. data migration Plan | 1. Data load into target as per plan 2. Customer to check data in target for duplicates & correctness | Data loaded into target | Data verified and signed Off by Customer
Prod Migration | BA, Architect, Tech Lead, Test Analyst, PM | UAT Sign Off | 1. Meta data migration 2. Data migration 3. User Setup 4. Integration Interface(s) setup 5. Smoke test | Production box ready with code and data | Users live in Production
Post Go-Live Support | BA, Developer, Test Analyst | Application live on Production | 1. Issue Analysis 2. Issue Fix, Test and migration to Prod 3. Hand over to Support team | 1. Post-Go -Live- Kick Off 2. Defect Fixes 3. Guiding Users to Training documents for Training Issues | End of Support Phase

## RolesResponsibilites
Sl.No | Activity | Ownership
1 | Project initiation,Project plan | Project Manager/Delivery Manager
2 | Discovery, User stories, EPIC, functional requriements document | Business Analyst
3 | Technical design document, HDD,LLD, Code review, Traceability Matrix, deployment plan | Technical Architect/Technical Lead
4 | Development, unit testing | Developer
5 | Test Cases, Testing, Test Script,Traceability Matrix | QA
6 | Test plan, Test strategy,Traceability Matrix | QA Lead
7 | Project functional validation as per requriements | Business Analyst
8 | UAT defects ( validation, fixing) | QA, Developer
9 | Business demo | QA, Business Analyst
10 | Change process/Release process | Technical Architect/Technical Lead. Project manager
11 | Deployment/Production Release | Release Team/Developer/Technical lead/Technical Architect
12 | Requriements sign off, UAT Sign off | Business Analyst,Project manager
13 | Training business on product usage, Training document | Business Analyst, Technical writer
14 | Post Go-live support | QA, Developer, technical lead,Business Analyst