## Trading (Drop1)
Module Description | Loose |  |  |  | HBC |  |  |  | H&T |  |  |  | SPF |  |  |  |  | MT/HoReCa |  | H&T | SPF | Bio-Diesel | Loose
| Feature Applicable | Discovery | Development | Resource | Applicable | Discovery | Development | Resource | Applicable | Discovery | Development | Resource | Applicable | Discovery | Development | Resource | Applicable | Discovery | Development
Price Roll Out | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes | TT Creation | TT Creation | Price Roll Out | Price Roll Out
1. Add Premium ( NSM & ZH) | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes | Quick Booking | Quick Booking | TT Creation | TT Creation
2. Add Customized Discount and additional premium ( NSM) | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes | Add Premium | Add Premium | Quick Booking | Quick Booking
3. Cost Component Addition | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes | Daily allocation | Daily allocation | Reports |  | In Progress (Sign Off Pending)
4. Ability to Favourate Discount Rules | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes (NSM) | Yes | Yes | additional allocation in quick order booking. | additional allocation in quick order booking. |  |  | Discovery & Sign Off Completed
5. State & Region Wise Roll out ability | No | NA | NA | Vandana | No | NA | NA | Anirudh | No | NA | NA | Anirudh | No | NA | NA | Anirudh | No | NA | NA | Set Discounts & Add additional premium | Set Discounts & Add additional premium
Price Roll out View | No | NA | NA | Vandana | Yes | Yes - Price Rollout State-wise | In Progress | Vandana | Yes | Yes | In Progress | Vandana | Yes | Yes | In Progress | Vandana | Yes | Yes | In Progress | View Sauda Bookings reports | View Sauda Bookings reports
Price Roll out download | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes | Sauda Approval & View Margin | Sauda Approval & View Margin
Trader Price Request | Yes | Yes | Yes |  | No | NA | NA | Umair | No | NA | NA | Umair | No | NA | NA | Umair | No | NA | NA
Price Request Approval | Yes | Yes | Yes |  | No | NA | NA | Umair | No | NA | NA | Umair | No | NA | NA | Umair | No | NA | NA
Daily allocation | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes | Yash | Yes | CR | Not Started | Price Roll out download | Price Roll out download
Quick Order Booking | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | CR | Not Started | Quick Order Booking | Quick Order Booking
Additional allocation in quick order booking. | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | CR | Not Started | PTD & MOP | PTD & MOP
PTD & MOP | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes | Sauda Booking | Sauda Booking
Sauda Booking | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes | Sauda Limit Increase | Sauda Limit Increase
Sauda Approval & View Margin ( NSM while approval) | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes | Sauda Conversions/Cancellation/Buy Back/Extension | Sauda Conversions/Cancellation/Buy Back/Extension
Sauda Allocation(Only HBC) | No | NA | NA | Vandana | Yes | Yes | Yes |  | No | NA | NA | Yash | No | NA | NA | Yash | No | NA | NA | Indentation | Indentation
Sauda Agreement Creation | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes | Sauda limit - Edit & Approval | Sauda limit - Edit & Approval
SRM TT Submission | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes - Same as vertical | Yes | Yes | Spot Sauda | Spot Sauda
TT Creation | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes | Reports | Reports
Sauda Agreement Submition to SAP | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
Updation of Contract No. & TT No. on Sauda Agreement. | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
View Sauda Bookings reports | Yes | Yes | In Progress | Vandana | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress
Sauda Limit Increase - Request (BDO & Customer in dealer App) | Yes | Yes | In Progress |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | In Progress
Sauda limit - Edit & Approval ( BDO & ZH) | Yes | Yes | In Progress |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
Indentation | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
Spot Sauda - Inform to Admin Verbally | Yes | Yes | In Progress |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
Unpunched Sauda | Yes | Yes | In Progress | Vandana | Yes | Yes | In Progress | Umair | Yes | Yes | In Progress | Umair | Yes | Yes | In Progress |  | Yes | Yes | In Progress
Sauda Conversions - Customer to Customer | Yes | Yes | Yes | Vandana | No | NA | NA | Umair | No | NA | NA | Umair | No | NA | NA | Umair | No | No
Sauda Conversions- Material To Material | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | No | NA | NA | Sohail | Yes | Yes | Yes
Sauda Conversions- TBHQ | Yes | Yes | Yes | Vandana | No | NA | NA | Sohail | No | NA | NA | Sohail | No | NA | NA | Sohail | No | NA | NA
Sauda Conversions- Incoterm | No | NA | NA | Vandana | Yes | Yes | Yes |  | No | NA | NA | Sohail | No | NA | NA | Sohail | No | NA | NA
Sauda Conversions- Plant to depot / depot To Plant | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
Sauda Conversions - Depot to depot | No | NA | NA | Vandana | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
Sauda Cancellation (Admin) | NO - Only Min qty cancellation by admin | Yes | Partial- SAP remaining |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes- Partial |  | Yes | YEs | Yes
Sauda Buy Back | Yes | Yes | Yes | Vandana | No | NA | NA | Vandana | No | NA | NA | Vandana | No | NA | NA | Vandana | No
Sauda Extension | Yes | Yes | Yes | Vandana | No | NA | NA | Vandana | Yes | Yes | Yes | Vandana | Yes | Yes | Yes | Vandana | Yes | Yes | Yes
AI Nudges & SKU Recommendations | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress
Schemes | Yes - Price Protection | Yes | Yes | Harsh | Yes | Yes | Yes (As per current req) |  | Yes | Yes | Yes (As per current req) |  | No | NA | NA |  | Yes | Yes | In Progress
Target Vs Achievement & Incentives | Yes | Yes | Yes (As Per current req) | Harsh | Yes | Yes | Yes (As per current req) | Harsh | Yes | Yes | Yes | Harsh | Yes | Yes | Yes |  | Yes | Yes | Yes (as per current req)
H&T CP Sauda | No | NA | NA |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress
1. Admin Control area | No | NA | NA |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress
2. Sauda | No | NA | NA |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress
Hierarchy Role and Functionality | Yes | Yes | Yes (As Per current req) |  | Yes | Yes | Yes (As per current req) |  | Yes | Yes | Yes (As per current req) |  | Yes | Yes | Yes (as per current req) |  | Yes | Yes | Yes (as per current req)
Hierarchy Role and Functionality - New Persona | Yes | Yes | In Progress |  | Yes | Yes | No |  | Yes | Yes | In Progress |  | Yes | Yes | In Progress |  | Yes | Yes | Not Started
Communication - Marketing | Yes | Yes | In Progress (Case has been raised with SF) |  | Yes | Yes | In Progress (Case has been raised with SF) |  | Yes | Yes | In Progress(Case has been raised with SF) |  | Yes | Yes | In Progress (Case has been raised with SF) |  | Yes | Yes | In Progress (Case has been raised with SF)
Communication - Internal | Yes | Yes | Yes | Ishan | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
Integration | All Trading Verticals
Touchpoint | Discovery | Development | Resource
Product Master Sync | Yes | Yes
Customer Master Sync | Yes | Yes
Plant/Depot Master | Yes | Yes
Unit of Measure (UOM) Sync | Yes | Yes
Sauda Booking/Creation | Yes | Yes
TT Generation Request | Yes | Yes
Sauda Release | Yes | Yes
Sauda Conversion | Yes | Yes
Sauda Sales contract creation response | Yes | Yes
Sauda Buyback | Yes | Yes
Sauda Cancellation | Yes | Yes
Sauda Extension | Yes | Yes
Lift Indent Request(IQ) | Yes | Yes
Order Status Update | Yes | Yes
Credit Limit | Yes | Yes
SF Access token | Yes | Yes
MTM Report for Sauda /cancel/Buyback | Yes | Yes
Spot Sauda | Yes | Yes
Price Protection | Yes | Yes
Truck Details | Yes | Yes
Invoice Change | Yes | Yes
Sauda Cancellation without Credit Notes | Yes | Yes
Product Change (Weight) | Yes | Yes
TT Generation Request (Manufacturing Plant) - Bio Diesel | Yes | No
Overdue Report | Yes - ETA-29/10(Umair) | In Progress
Sauda Sync | Yes (6/11) | No

## Non-Trading(Drop 2)
Module Description | H&T |  |  |  | MT |  |  |  | HoReCa |  |  |  | E-Comm
| Feature Applicable | Discovery | Development | Resource | Feature Applicable | Discovery | Development | Resource | Feature Applicable | Discovery | Development | Resource | Feature Applicable | Discovery | Development | Resource
Setup Pricing In DMS | Yes | Yes | Yes | Varun/Vinod (Margin Master Awaited) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Scheme DMS | Yes | Yes | In Progress | Varun (Eligebility Criteria to be shared) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
L1 And L2 | Yes | Yes | In Progress | Vinod (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Primary Order | Yes | Yes | Yes | Vinod (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Secondary Order | Yes | Yes | Yes | Vinod (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Fulfill Secondary Order | Yes | Yes | Yes | Vinod (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Primary Invoice | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Seconary Invoice | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Approve Primary Order From SO And ASM | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Primary Return | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Secondary Return | Yes | Yes | Yes | Vinod (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Approve Secodary Return | Yes | Yes | Yes | Vinod (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
DMS Inventory | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
DMS GRN | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Damage Claim | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR Claim | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Secondary Scheme Claim | Yes | Yes | Yes | Vinod (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Super Stockist freight claim | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
No Dues Certificate | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Ledger | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Primary Credit/Debit Note | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Secondary Credit/Debit Note | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Generate Load Sheet | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Collect Payment In DMS | Yes | Yes | Yes | Vinod (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Approve Collection In DMS | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Reports And Dashboard’s | Yes | Yes | In Progress | Vinod (Consultant Approach) | No | N/A | N/A |  | No | N/A | N/A |  | Yes | Yes | In Progress | Harsh
Batch for Secondary Order Reject after 3 Days | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Batch for Reject Pending Orders Last Day of the month | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR Route Planning | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
ASO Route Planning | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO Route Planning | Yes | Yes | Yes | Vinod (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Admin - Survey Form Management | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Admin - Sub DB Onboarding Form Management | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Admin - SR Onboarding Form Management | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Admin - DB Onboarding Form Management | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR/SO/ASO - IMEI Verification | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR/SO/ASO-Attendence Capture | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR/SO/ASO-Field Visit | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Ad-Hoc Visit | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR-Secondary Order For Retailer | Yes | Yes | In Progress | Ankit (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Scheme In SR App | Yes | Yes | Yes | Ankit | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR-Secondary Return For Retailer | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR-Collection | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR-Survey | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR-Setup Pricing For Secondary Order | Yes | Yes | Yes | Ankit (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR-Setup Pricing For Secondary Return | Yes | Yes | Yes | Ankit (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SR- Retailer Onboarding | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
ASO - SubDB Stock capture | Yes | Yes | Yes | Ankit (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
ASO -Secondary Return For Sub DB | Yes | Yes | In Progress | Ankit (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
ASO -Secondary Order For Sub DB | Yes | Yes | In Progress | Ankit (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
ASO -Secondary Order For Retailer | Yes | Yes | In Progress | Ankit (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Admin Work Activity | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Individual Market Work | Yes | Yes | Yes | Ankit (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Market and DB Visit | Yes | Yes | Yes | Ankit (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Meetings | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Prospecting/ Vacant SR DB-Visit | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Weekly-off/Holiday | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Secondary Order For Retailer | Yes | Yes | Yes | Ankit (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Stock Check | Yes | Yes | Yes | Ankit (L1/L2 Changes) | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Competitor tracking | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO- Retailer Onboarding | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Survey | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Scheme In SO App | Yes | Yes | Yes | Ankit | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Setup Pricing For Secondary Order | Yes | Yes | Yes | Ankit | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
SO-Setup Pricing For Secondary Return | Yes | Yes | Yes | Ankit | No | N/A | N/A |  | No | N/A | N/A |  | No | N/A | N/A
Merchandising Activity | No | N/A | N/A |  | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A
Exception creation | No | N/A | N/A |  | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A
Exception view | No | N/A | N/A |  | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A
Growth mapping | No | N/A | N/A |  | Yes | Yes | Yes |  | No | N/A | N/A |  | No | N/A | N/A
Sauda booking [Anirudh-Umair] | No | N/A | N/A |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | No | N/A | N/A
Leads Vs Opportunities | No | N/A | N/A |  | Yes | Yes | Yes | Varun (Recent Changes) | Yes | Yes | Yes |  | No | N/A | N/A
Primary Order [Internal Walkthrough Pending] | No | N/A | N/A |  | Yes | Yes | Yes | Vinod & kiru | Yes | Yes | Yes |  | No | N/A | N/A
Order Posting through whats App and mail | No | N/A | N/A |  | Yes | Yes | In Progress | Ishan & kiru | No | N/A | N/A |  | No | N/A | N/A
Secondary order | No | N/A | N/A |  | No | N/A | N/A |  | Yes | Yes | Yes |  | No | N/A | N/A
Target Vs Achivements | Yes | Yes | Yes |  | Yes | No | Not Started | Varun | Yes | Yes | In Progress | Varun | No | N/A | N/A
Horeca SO Market work Capture (Online) | No | N/A | N/A |  | No | N/A | N/A |  | Yes | Yes | In Progress | Varun
Price Benchmarking - Food | Yes | Yes | In Progress |  | Yes | Yes | In Progress | Harsh | Yes | Yes | In Progress | Harsh
Price Benchmarking - Oil | Yes | Yes | Yes |  | Yes | Yes | Yes | Harsh | Yes | Yes | In Progress | Harsh
AI Nudges | Yes | Yes | In Progress |  | No | N/A | N/A |  | No | N/A | N/A
SAP Integration | All Non Trading Verticals
Product | Feature Applicable | Discovery | Development | Resource
Tableau -->SAP (Pricing) | Yes | Yes | Yes | Harsh
SAP-->SF(Pricing) | Yes | Yes | Yes
Distributor / Customer Master/Incoterm | Yes | Yes | Yes
Primary Orders | Yes | Yes | Yes
Invoice | Yes | Yes | Yes
Returns | Yes | Yes | Yes
Credit Notes | Yes | Yes | Yes
Credit Limit/Credit Days | Yes | Yes | Yes
Bank Guarantee / Credit Control | Yes | Yes | Yes
Deposit Report ETA - [29 Oct 2025] | Yes | No | No
Claims posting | Yes | Yes | In Progress

## Sheet2
[6 empty] | Applicable | Discovery | Development
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | No | NA | NA
[6 empty] | Yes | Yes | In Progress
[6 empty] | Yes | Yes | Yes
[6 empty] | No | NA | NA
[6 empty] | No | NA | NA
|  | \ |  |  |  | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | No | No | No
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | In Progress
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | In Progress
[6 empty] | No | NA | NA
[6 empty] | Yes | Yes | Yes
[6 empty] | No | NA | NA
[6 empty] | No | No | No
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | Yes
[6 empty] | No | NA | NA
[6 empty] | Yes | Yes | Yes
[6 empty] | Yes | Yes | In Progress
[6 empty] | Yes | No | In Progress
[6 empty] | Yes | Yes | In Progress
[6 empty] | Yes | Yes | In Progress
[6 empty] | Yes | Yes | In Progress
[6 empty] | Yes | Yes | In Progress
[6 empty] | Yes | Yes | Yes (As per current req)
[6 empty] | Yes | No-ETA - 28/10 | In Progress
[6 empty] | Yes | Yes | In Progress(Case has been raised with SF)
[6 empty] | Yes | Yes | Yes
Vertical | Total No of Modules | Discovery Completed | Discovery Completion % | Development Completion % | Development In Progress %
HBC | 24 | 21 | 87.5 | 66.7% | 33.3%

## Pivot
Vertical | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
HBC | 40 | 40 | 100% | 31 | 77.5% | 8 | 20% | 1 | 2
Vertical | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
Loose | 24 | 24 | 100% | 17 | 70.83% | 7 | 29% | 0 | 0%
Vertical | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
H&T | 39 | 39 | 100% | 30 | 76.92% | 9 | 23.08% | 0 | 0%
Vertical | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
SPF | 38 | 38 | 100% | 29 | 76.32% | 9 | 23.68% | 0 | 0%
Vertical | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
MT/HoReCa | 39 | 39 | 100% | 24 | 61% | 14 | 35.9% | 1 | 2.564%
Integration | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
Drop 1 Integration | 25 | 25 | 100% | 23 | 92% | 1 | 4% | 1 | 4
Vertical | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
H&T | 69 | 69 | 100% | 60 | 86.96% | 9 | 13.04% | 0 | 0%
Vertical | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
MT | 11 | 11 | 100% | 8 | 72.73% | 2 | 18.18% | 1 | 9.091%
Vertical | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
HoReCa | 8 | 8 | 100% | 4 | 50% | 3 | 37.5% | 1 | 12%
Vertical | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
Ecomm | 1 | 1 | 100% | 0 | 0% | 1 | 100% | 0 | 0%
Integration | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
Drop 2 Integration | 9 | 9 | 100% | 9 | 100% | 0 | 0% | 0 | 0%
Admin App | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
Admin App | 23 | 23 | 100% | 23 | 100% | 0 | 0% | 0 | 0%
Dealer App | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
Dealer App | 10 | 10 | 100% | 6 | 60% | 4 | 40% | 0 | 0%
SDK App--H&T | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
SDK App--H&T | 33 | 33 | 100% | 33 | 100% | 0 | 0% | 0 | 0%
SDK App--MT | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
SDK App--MT | 13 | 13 | 100% | 13 | 100% | 0 | 0% | 0 | 0%
Bio Diesel | Total No of Modules/Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
Bio Diesel | 6 | 6 | 100% | 2 | 33.33% | 4 | 66.67% | 0 | 0%
Overall Integration | Total No of Modules | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
Drop 1 & Drop 2 Integration | 34 | 34 | 100 | 32 | 94.12% | 2 | 5.882% | 0 | 0%
Overall SDK App | Total No of Modules | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
Overall SDK App | 46 | 46 | 100% | 46 | 100% | 0 | 0% | 0 | 0%
Overall Build Status | Total No of Features | Discovery Completed | Discovery Completion % | Development Completed | Development Completion % | Development In Progress | Development In Progress % | Development Not Started | Development Not Started %
Overall Build Status (Drop 1 & Drop 2) | 388 | 387 | 99% | 330 | 90% | 54 | 14% | 4 | 1.031%

## Bio Diesel
Bio Diesel
Modules | Feature Applicable | Discovery | Development
Tender Creation | Yes | Yes | Yes
Tender Allocation | Yes | Yes | In Progress (Last minute Changes to be incorporated)
SRM TT Submition | Yes | Yes | In Progress (Last minute Changes to be incorporated)
Sauda Creation | Yes | Yes | In Progress (Last minute Changes to be incorporated)
Terminal Coordinator App | Yes | Yes | Yes
Reports | Yes | Yes | In Progress (Last minute Changes to be incorporated)

## Discovery - Non Trading(Drop 2) (hidden)
Verticals | H&T | MT | HoReCa | Loose/SPF | HBC | H&T | E-Comm | SAP Integration
Kiru / Sakshi / Aditi | DMS | Merchandising Activity | Secondary order [Internal Walkthrough Pending] | Target Vs Achivements | Target Vs Achivements ETA -[28 Oct 2025] | Target Vs Achivements | Reports & Dashboards | Product
| Setup Pricing In DMS |  |  | Phasing Eligibility - Criteria | Phasing Eligibility - Criteria ETA -[28 Oct 2025] |  |  | Tableau -->SAP (Pricing)
| Scheme DMS | Exception creation | Lead generation |  | Schemes - Walkthrough with PS team - In progress |  |  | SAP-->SF(Pricing)
| L1 And L2 | Exception view | Sauda booking [Anirudh-Umair] |  |  | Price & Margin master |  | Distributor / Customer Master/Incoterm
| Primary Order | Growth mapping | Primary Order [Internal Walkthrough Pending] |  |  |  |  | Primary Orders
| Secondary Order | Sauda booking [Anirudh-Umair] | Leads and Opportunities |  |  |  |  | Invoice
| Fulfill Secondary Order | Leads Vs Opportunities | [5 empty] | Returns | Need Clarity
| Primary Invoice | Secondary order | [5 empty] | Credit Notes | Out Off Scope
| Seconary Invoice | Primary Order [Internal Walkthrough Pending] | [5 empty] | Claims | Work Not Started
| Approve Primary Order From SO And ASM | Order Posting through whats and mail | [5 empty] | Credit Limit/Credit Days | Completed In Dev
| Primary Return | [6 empty] | Bank Guarantee / Credit Control | Dont Have Requirment
| Secondary Return | [6 empty] | Deposit Report ETA - [29 Oct 2025] | Master Not Received
| Approve Secodary Return | [6 empty] | Claims posting | Work In Progress
| DMS Inventory | [7 empty] | Requirement Gathered, Dev is Pending
DMS GRN
Damage Claim
SR Claim
Secondary Scheme Claim
Super Stockist freight claim
No Dues Certificate
Ledger
Primary Credit/Debit Note
Secondary Credit/Debit Note
Generate Load Sheet
Collect Payment In DMS
Approve Collection In DMS
Reports And Dashboard’s
Batch for Secondary Order Reject after 3 Days
Batch for Reject Pending Orders Last Day of the month
SFA
SR Route Planning
ASO Route Planning
SO Route Planning
Admin - Survey Form Management
Admin - Sub DB Onboarding Form Management
Admin - SR Onboarding Form Management
Admin - DB Onboarding Form Management
SR/SO/ASO - IMEI Verification
SR/SO/ASO-Attendence Capture
SR/SO/ASO-Field Visit
Ad-Hoc Visit
SR-Secondary Order For Retailer
Scheme In SR App
SR-Secondary Return For Retailer
SR-Collection
SR-Survey
SR-Setup Pricing For Secondary Order
SR-Setup Pricing For Secondary Return
SR- Retailer Onboarding
ASO - SubDB Stock capture
ASO -Secondary Return For Sub DB
ASO -Secondary Order For Sub DB
ASO -Secondary Order For Retailer
SO-Admin Work Activity
SO-Individual Market Work
SO-Market and DB Visit
SO-Meetings
SO-Prospecting/ Vacant SR DB-Visit
SO-Weekly-off/Holiday
SO-Secondary Order For Retailer
SO-Stock Check
SO-Competitor tracking
SO- Retailer Onboarding
SO-Survey
Scheme In SO App
SO-Setup Pricing For Secondary Order
SO-Setup Pricing For Secondary Return

## Build - Non Trading(Drop 2) (hidden)
Verticals > | H&T | MT | HoReCa | HBC/Loose/SPF | E-Comm
| Target Vs Achivements | Merchandising Activity | Secondary order | Target Vs Achivements | Reports & Dashboards
| Approve primary order | Exception creation | Lead generation
| Create primary order | Exception view | Sauda booking |  |  | In Progress
| Field visit | Growth mapping | Primary order |  |  | Build Complete
| Joint working | Sauda booking | Leads and Opportunities
| Prospecting | Leads Vs Opportunities
| Admin | Secondary order
| Competitor tracking | Primary Order
On board SR
Create Primary order
Accept GRN
Create SDR Claims
Create Primary returns
Approve secondary returns
Create credit/Debit notes
Create NDC
Create Claims
Inventory transfer
Create invoice
Create load generation sheet
Create Secondary order
Collection and Collection Approval
Visit retailer
Order taking
Collections
Collect returns
Visit SubD
Invetory check - SubD
Retailer Order
SubD Primary order
L1/L2

## Discovery - Trading(Drop 1) (hidden)
Verticals > | HBC | H&T | SPF | Bio-Diesel | Loose
Rahul / Sakshi / Aditi | TT Creation | TT Creation | TT Creation | Price Roll Out | Price Roll Out
| Quick Booking | Quick Booking | Quick Booking | TT Creation | TT Creation
| Add Premium | Add Premium | Add Premium | Quick Booking | Quick Booking
| Daily allocation | Daily allocation | Daily allocation | Reports |  | In Progress (Sign Off Pending)
| additional allocation in quick order booking. | additional allocation in quick order booking. | additional allocation in quick order booking. |  |  | Discovery & Sign Off Completed
| Set Discounts & Add additional premium | Set Discounts & Add additional premium | Set Discounts & Add additional premium
| View Sauda Bookings reports | View Sauda Bookings reports | View Sauda Bookings reports
| Sauda Approval & View Margin | Sauda Approval & View Margin | Sauda Approval & View Margin
| Price Roll out download | Price Roll out download | Price Roll out download
| Quick Order Booking | Quick Order Booking | Quick Order Booking
| PTD & MOP | PTD & MOP | PTD & MOP
| Sauda Booking | Sauda Booking | Sauda Booking
| Sauda Limit Increase | Sauda Limit Increase | Sauda Limit Increase
| Sauda Allocation(Only HBC) | Sauda Conversions/Cancellation/Buy Back/Extension | Sauda Conversions/Cancellation/Buy Back/Extension
| Sauda Conversions/Cancellation/Buy Back/Extension | Indentation | Indentation
| Indentation | Sauda limit - Edit & Approval | Sauda limit - Edit & Approval
| Sauda limit - Edit & Approval | Spot Sauda | Spot Sauda
| Spot Sauda - Inform to Admin Verbally | Reports | Reports
Reports

## Build - Trading(Drop 1) (hidden)
Verticals > | HBC | Testcase QA/SIT | Testing QA/SIT | H&T | SPF | Bio-Diesel | Loose
| TT Creation | QA | QA | TT Creation | TT Creation | Price Roll Out | Price Roll Out
| Quick Booking | SIT | SIT | Quick Booking | Quick Booking | TT Creation | TT Creation
| Add Premium | QA/SIT | QA/SIT | Add Premium | Add Premium | Quick Booking | Quick Booking
| Daily allocation |  |  | Daily allocation | Daily allocation | Reports
| Additional allocation in quick order booking. |  |  | Additional allocation in quick order booking. | Additional allocation in quick order booking.
| Set Discounts & Add additional premium |  |  | Set Discounts & Add additional premium | Set Discounts & Add additional premium |  |  | In Progress
| View Sauda Bookings reports |  |  | View Sauda Bookings reports | View Sauda Bookings reports |  |  | Build Complete
| Sauda Approval & View Margin |  |  | Sauda Approval & View Margin | Sauda Approval & View Margin
| Price Roll out download |  |  | Price Roll out download | Price Roll out download
| Quick Order Booking |  |  | Quick Order Booking | Quick Order Booking
| PTD & MOP |  |  | PTD & MOP | PTD & MOP
| Sauda Booking |  |  | Sauda Booking | Sauda Booking
| Sauda Limit Increase |  |  | Sauda Limit Increase | Sauda Limit Increase
| Sauda Allocation(Only HBC) |  |  | Sauda Conversions/Cancellation/Buy Back/Extension | Sauda Conversions/Cancellation/Buy Back/Extension
| Sauda Conversions/Cancellation/Buy Back/Extension |  |  | Indentation | Indentation
| Indentation |  |  | Sauda limit - Edit & Approval | Sauda limit - Edit & Approval
| Sauda limit - Edit & Approval |  |  | Spot Sauda | Spot Sauda
| Spot Sauda |  |  | Reports | Reports
Reports

## SDK App
Module Description | H&T |  |  |  | MT
| Feature Applicable | Discovery | Development | Resource | Feature Applicable | Discovery | Development | Resource
Setup Pricing In DMS | No | NA | NA |  | No | NA | NA
Scheme DMS | No | NA | NA |  | No | NA | NA
L1 And L2 | No | NA | NA |  | No | NA | NA
Primary Order | No | NA | NA |  | No | NA | NA
Secondary Order | Yes | Yes | Yes |  | No | NA | NA
Fulfill Secondary Order | No | NA | NA |  | No | NA | NA
Primary Invoice | No | NA | NA |  | No | NA | NA
Seconary Invoice | Yes | Yes | Yes |  | No | NA | NA
Approve Primary Order From SO And ASM | No | NA | NA |  | No | NA | NA
Primary Return | No | NA | NA |  | No | NA | NA
Secondary Return | Yes | Yes | Yes |  | No | NA | NA
Approve Secodary Return | No | NA | NA |  | No | NA | NA
DMS Inventory | No | NA | NA |  | No | NA | NA
DMS GRN | No | NA | NA |  | No | NA | NA
Damage Claim | No | NA | NA |  | No | NA | NA
SR Claim | No | NA | NA |  | No | NA | NA
Secondary Scheme Claim | No | NA | NA |  | No | NA | NA
Super Stockist freight claim | No | NA | NA |  | No | NA | NA
No Dues Certificate | No | NA | NA |  | No | NA | NA
Ledger | No | NA | NA |  | No | NA | NA
Primary Credit/Debit Note | No | NA | NA |  | No | NA | NA
Secondary Credit/Debit Note | No | NA | NA |  | No | NA | NA
Generate Load Sheet | No | NA | NA |  | No | NA | NA
Collect Payment In DMS | No | NA | NA |  | No | NA | NA
Approve Collection In DMS | No | NA | NA |  | No | NA | NA
Reports And Dashboard’s | No | NA | NA |  | No | NA | NA
Batch for Secondary Order Reject after 3 Days | No | NA | NA |  | No | NA | NA
Batch for Reject Pending Orders Last Day of the month | No | NA | NA |  | No | NA | NA
SR Route Planning | No | NA | NA |  | No | NA | NA
ASO Route Planning | No | NA | NA |  | No | NA | NA
SO Route Planning | No | NA | NA |  | No | NA | NA
Admin - Survey Form Management | No | NA | NA |  | No | NA | NA
Admin - Sub DB Onboarding Form Management | No | NA | NA |  | No | NA | NA
Admin - SR Onboarding Form Management | No | NA | NA |  | No | NA | NA
Admin - DB Onboarding Form Management | No | NA | NA |  | No | NA | NA
SR/SO/ASO - IMEI Verification | Yes | Yes | Yes |  | Yes | Yes | Yes
SR/SO/ASO-Attendence Capture | Yes | Yes | Yes |  | Yes | Yes | Yes
SR/SO/ASO-Field Visit | Yes | Yes | Yes |  | Yes | Yes | Yes
Ad-Hoc Visit | Yes | Yes | Yes |  | Yes | Yes | Yes
SR-Secondary Order For Retailer | Yes | Yes | Yes |  | No | NA | NA
Scheme In SR App | Yes | No | No |  | No | NA | NA
SR-Secondary Return For Retailer | Yes | Yes | Yes |  | No | NA | NA
SR-Collection | Yes | Yes | Yes |  | No | NA | NA
SR-Survey | Yes | Yes | Yes |  | No | NA | NA
SR-Setup Pricing For Secondary Order | No | NA | NA |  | No | NA | NA
SR-Setup Pricing For Secondary Return | No | NA | NA |  | No | NA | NA
SR- Retailer Onboarding | Yes | Yes | Yes |  | No | NA | NA
ASO - SubDB Stock capture | Yes | Yes | Yes |  | No | NA | NA
ASO -Secondary Return For Sub DB | Yes | Yes | Yes |  | No | NA | NA
ASO -Secondary Order For Sub DB | Yes | Yes | Yes |  | No | NA | NA
ASO -Secondary Order For Retailer | Yes | Yes | Yes |  | No | NA | NA
SO-Admin Work Activity | Yes | Yes | Yes |  | No | NA | NA
SO-Individual Market Work | Yes | Yes | Yes |  | No | NA | NA
SO-Market and DB Visit | Yes | Yes | Yes |  | No | NA | NA
SO-Meetings | Yes | Yes | Yes |  | No | NA | NA
SO-Prospecting/ Vacant SR DB-Visit | Yes | Yes | Yes |  | No | NA | NA
SO-Weekly-off/Holiday | Yes | Yes | Yes |  | No | NA | NA
SO-Secondary Order For Retailer | Yes | Yes | Yes |  | No | NA | NA
SO-Stock Check | Yes | Yes | Yes |  | Yes | Yes | Yes
SO-Competitor tracking | Yes | Yes | Yes |  | Yes | Yes | Yes
SO- Retailer Onboarding | Yes | Yes | Yes |  | No | NA | NA
SO-Survey | Yes | Yes | Yes |  | No | NA | NA
Scheme In SO App | Yes | Yes | Yes |  | No | NA | NA
SO-Setup Pricing For Secondary Order | No | NA | NA |  | No | NA | NA
SO-Setup Pricing For Secondary Return | No | NA | NA |  | No | NA | NA
Merchandising Activity | No | NA | NA |  | Yes | Yes | Yes
Exception creation | No | NA | NA |  | Yes | Yes | Yes
Exception view | No | NA | NA |  | Yes | Yes | Yes
Growth mapping | No | NA | NA |  | Yes | Yes | Yes
Sauda booking [Anirudh-Umair] | No | NA | NA |  | No | NA | NA
Leads Vs Opportunities | No | NA | NA |  | No | NA | NA
Secondary order | Yes | Yes | Yes |  | No | NA | NA
Primary Order [Internal Walkthrough Pending] | No | NA | NA |  | No | NA | NA
Order Posting through whats App and mail | No | NA | NA |  | No | NA | NA
Lead generation | No | NA | NA |  | No | NA | NA
Sauda booking | No | NA | NA |  | No | NA | NA
Leads and Opportunities | No | NA | NA |  | No | NA | NA
Target Vs Achivements | Yes | Yes | Yes |  | Yes | Yes | Yes
Phasing Eligibility - Criteria | No | NA | NA |  | No | NA | NA
Price & Margin Master | No | NA | NA |  | No | NA | NA
Reports And Dashboard’s | Yes | Yes | Yes |  | Yes | Yes | Yes
Horeca SR + SO Market work Capture (Online) | No | NA | NA |  | No | NA | NA
END DAY | Yes | Yes | Yes |  | Yes | Yes | Yes

## Apps (Admin & Dealer)
Dealer App | Feature Applicable | Discovery | Development | Resource | Admin App | Feature Applicable | Discovery | Development | Resource
1. (Display Sauda Limit &Available Sauda Limit) | Yes | Yes | Yes |  | 1. Update & View Eal user, Customer Details , & Ship to Party Details with Search and Filter option ( Vertical, ZH, State, District & City ) | Yes | Yes | Yes
2. Sauda limit enhancement and sauda creation request | Yes | Yes | Yes |  | 2.Update & View Broker Details with Search and Filter option ( Vertical, ZH, State, District & City ) | Yes | Yes | Yes
3. Indent request creation | Yes | Yes | Yes |  | 3.Mapping of BDO with Delaler, Dealer and Broker, Dealer of Ship to Party. | Yes | Yes | Yes
4. Competitor tracking - PTD/MOP | Yes | Yes | Yes |  | 4.View Price Screen -> Selection ->> Vertical - ZH-BDO- Search & Display Dealer - Plant/Depot - Incoterm -Multiple Oil Type ->>>Show Price for all active SKU for which Price released and not released | Yes | Yes | Yes
5. Survey | Yes | Yes | In Progress |  | 5.Material Cost update for all vertical & Price Generation(Final price generate button on app) -(Loose oil price) | Yes | Yes | Yes
6. Message broadcasting & ticker | Yes | Yes | In Progress |  | 6.Freight mater update | Yes | Yes | Yes
7. Support | Yes | Yes | In Progress |  | 7.Sauda list view | Yes | Yes | Yes
8. Claims | Yes | Yes | Yes |  | 8.Sauda Limit Update | Yes | Yes | Yes
9. NDC | Yes | Yes | Yes |  | 9.Sauda Limit Utilization Checking & Update | Yes | Yes | Yes
10. Bank guarantee status | Yes | Yes | In Progress |  | 10.Indent request Status and Re-process Option ( If Failed ) | Yes | Yes | Yes
[5 empty] | 11.Sauda Conversion and allocation Delta file update | Yes | Yes | Yes
[5 empty] | 12.Sauda Conversion List with status and re-process Option ( If failed ) | Yes | Yes | Yes
[5 empty] | 13.Conversion contract check with Vertical wise and conversion type wise with release / Unrelease option. | Yes | Yes | Yes
[5 empty] | 14.Contract extension & Validation date change Option | Yes | Yes | Yes
[5 empty] | 15.Competitor Master creation | Yes | Yes | Yes
[5 empty] | 16.Competitor price edit and delete Option | Yes | Yes | Yes
[5 empty] | 17.Booking Information edit and delete option | Yes | Yes | Yes
[5 empty] | 18.Sauda Report, Booking Information Report. Sales Report. | Yes | Yes | Yes
[5 empty] | 19.Minimum Quantity Contract Block Option | Yes | Yes | Yes
[5 empty] | 20.Vertical wise sauda booking stop | Yes | Yes | Yes
[5 empty] | 21.SKU Master | Yes | Yes | Yes
[5 empty] | 22.Discount approval on behalf of NSM (With margin & loose price view) | Yes | Yes | Yes
[5 empty] | 23.Stop Published Price. | Yes | Yes | Yes